## Slide 1
Digital Transformation
Program Key Improvements
25 June 2021

## Slide 2: Summary
Estimations unclear
Marketing enhancements SOW has several features with high estimates not aligning with M1 expectations.
Justifications for estimations were not documented at the time raising more questions.
Long time to release
The current time to release from the start of development to release is 10-13 weeks (for release 1.7).
Bottlenecks in UAT and accumulated testing backlog dating back to Supernova main factors.
Program efficiency not transparent
Program performance has been questioned and insight on program performance has been requested.
There is no undisputed data points available to measure development efficiency.
What led us to discuss these 3 key issue areas
What has been the trend
What was the tipping point
Why these specific 3 areas
Demand side changes – supply side changes
Salesforce ecosystem is at the core of the new platform and leveraging its out-of-the-box capabilities is the key for development efficiency
Context
3 Key Issue Areas
Establish an estimations factory with clear ways of working and supporting deliverables to estimations.
Provide sign offs and escalation path for in case of disputes.
3 Key Improvements
This planning is happening
Implement change management controls to reduce changes impacting releases through sprint merges.
Plan to accelerate release cycle especially through testing improvements and work on the enablers required.
This planning is happening
Provide a benchmark what was delivered, how much time and money has been invested
Establish an efficiency metric for the program to manage efficiency improvement
Discussed in detail 2 July
This presentation
To be filled together at the end

## Slide 3: Review of key marketing enhancement initiatives
xxx
Initiative |  | Original estimate | Scope | Rationale for complexity | Key component systems | Out-of-the-box capability | Remarks
1 | Pre-order |  |  |  |  |  | 
2 | Family plan | 1000 |  |  |  |  | 
3 | Revamp flexi |  |  |  |  |  | 
4 | Promo codes & Below the line discounts |  |  |  |  |  | 
Puneet

## Slide 4: Pre-order
xxx
Puneet
Based on input from component leads.
Scope
Customer is able to order a product that is not in the inventory for some future release date.
Touchpoints: microsite, agent console, eShop (delivery)
Processes: promotion, order, inventory, delivery, customer support, finance, operational reporting
Data model: virtual inventory, pre-order device creation and management
In subsequent releases: Order at shop, pick-up at shop, offline order submission, pre-order change handling
Rationale for complexity
Brand new flow and capability.
MVP version consists of 10 epics with 3 biggest ones:
  Pre-order flow at microsite
  Pre-order vouchers and promos
  Custom interface to inventory
Multiple systems impacted including D365 and eShop with the pre-order delivery dates.
Custom UX to be created for customer flows and customer support.
Queuing solution, performance and load management to be built.
Key component systems
Dynamics 365 virtual inventory management
AEM microsite new order flow for the pre-order for all the main flows PWD, PWI, new new, CBP, etc.
Agent console: providing customer support in I Buy flow and providing visibility to pre-order status
Vlocity XOM:
Vlocity CPQ/EPC: product modeling
Mulesoft: connecting the systems incl. eShop & D365
Sales console: firstly to process a new order type, secondly to be able to enable pick-up at shop
Remarks
1,040 person days was the original estimate for the full solution.
The MVP is estimated to be 488 person days.
The remaining effort for the full original scope is roughly 550 person days.
Remaining features include the retail enablement, incl. pick-up at shop and order at shop, and order change handling
Out-of-the-box capability
Dynamics 365: Inventory out of the box. Customization required to show info in agent console.
Vlocity CPQ/EPC: delivery slot management is custom built.
Mulesoft: New set of APIs to be created for the delivery slot management, legacy interaction and CPQ APIs
AEM microsite: full bespoke code as for rest of the products and flows.
Agent console: New information to be provided of pre-order status incl. a new queue and new interface for inventory – all custom.

## Slide 5: Flexi revamp
xxx
Definition of the feature as it is described
What are the additional complexities that got added (which you discovered in Discovery)
Details of the changes required at component level, what are the challenges
This slide is 100% editable. Adapt it to your needs and capture your audience's attention.
Add a % OOTB and what sort of customization required.
Also mention any other OOTB offered but this may not be an ask from M1
Puneet
Based on input from component leads.
Scope
Rationale for complexity
Key component systems
Remarks
Out-of-the-box capability

## Slide 6: Family plan
xxx
Definition of the feature as it is described
What are the additional complexities that got added (which you discovered in Discovery)
Details of the changes required at component level, what are the challenges
This slide is 100% editable. Adapt it to your needs and capture your audience's attention.
Add a % OOTB and what sort of customization required.
Also mention any other OOTB offered but this may not be an ask from M1
Puneet
Based on input from component leads.
Scope
Rationale for complexity
Key component systems
Remarks
Out-of-the-box capability

## Slide 7: Estimation factory
What is the model
How will it work
PI planning (quarterly) T-shirt size estimates (~ initiative level)
Discovery & Solutioning epic level estimates (used for sprint scope definition)
Sprint refinement story point estimates (used for final velocity and work planning)
Process
Who estimates (at each level) – how to include ISVs in a clever way
Where estimates are stored (Jira vs. Excels),
What documentation stored and where,
What is the sign-off process by PO,
How possible disputes are escalated
Akanksha to drive
Venkat, Puneet, Pinakini, Aaro,

## Slide 8: Tiger team
Who new vs. existing? Dedicated / not?
Is expected to do what
By when
How
Who invests?
Balu

## Slide 9: Actions & outcomes
Implement a pre-discovery phase where the requirement is conceptualized and iteratively developed – also with iterative estimations.
Provide the estimation justification and complexities.
xxx
Demand side (M1)
Xxx
Xxx
xxx
Actions
Outcomes
Xxx
Xxx
xxx
Supply side (Vendors)
Xxxx
Xxx
xxx
Establish a tiger team
Ensuring the change persists
Xxxx
Xxx
xxx
xxx
Mahesh, Balu, Subhash and team
Balu

## Slide 10: Effort estimation details

## Slide 11: Estimation Factory
Deep Dive - 3 for Three
Feature Envelope
Definition of the feature as it is described
Complexity of the Feature
What are the additional complexities that got added (which you discovered in Discovery)
Component details
Details of the changes required at component level, what are the challenges
Remarks
This slide is 100% editable. Adapt it to your needs and capture your audience's attention.
OOTB %
Add a % OOTB and what sort of customization required.
Also mention any other OOTB offered but this may not be an ask from M1
Puneet

## Slide 12: Estimation Factory
Deep Dive - 5G Booster
Feature Envelope
Definition of the feature as it is described
Complexity of the Feature
What are the additional complexities that got added (which you discovered in Discovery)
Component details
Details of the changes required at component level, what are the challenges
Remarks
This slide is 100% editable. Adapt it to your needs and capture your audience's attention.
OOTB %
Add a % OOTB and what sort of customization required.
Also mention any other OOTB offered but this may not be an ask from M1
Puneet

## Slide 13: Estimation Factory
Deep Dive - HUV Voucher
Feature Envelope
Definition of the feature as it is described
Complexity of the Feature
What are the additional complexities that got added (which you discovered in Discovery)
Component details
Details of the changes required at component level, what are the challenges
Remarks
This slide is 100% editable. Adapt it to your needs and capture your audience's attention.
OOTB %
Add a % OOTB and what sort of customization required.
Also mention any other OOTB offered but this may not be an ask from M1
Puneet

## Slide 14
THANK YOU
COPYRIGHT 2020 M1 LIMITED. ALL RIGHTS RESERVED.

## Slide 15: Content for 2 July

## Slide 16: 2+2 week release
Sprint | Sprint n-1 |  |  |  |  |  |  | Sprint n |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Sprint n+1 |  |  |  |  |  |  |  |  |  |  |  |  | 
Day | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SIT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
UAT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Milestones |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
SIT testing
UAT testing
Training
SOP writing
Test case prep
Test case prep
Go / no-go
Release
Scope fixed
For 2 July
Mahesh, Subhash,

## Slide 17: Enablers and their timeline to reach 2+2 week releases
Description
Impact
Parallel SIT with UAT
Perform SIT and UAT phases in parallel epic by epic – first select epics & tests, then all of them
Reduced dedicated duration for UAT
Timeline
Epic-based testing
Enable epic-based releases to SIT, UAT & other environments
Manage test suite and dependencies at epic level
Enable parallel testing of SIT and UAT epic by epic
Enable epic-based releases also to production
Timeline
Parallel SIT with Development
Perform SIT test cases in parallel with dev phase – first select tests, then all of them
Continuous dev, deploy, test cycle through the sprint
No need for Pre-SIT
Reduced dedicated duration for SIT
Timeline
Integrated dev environment
Dedicate one SIT environment to be the integrated dev env.
Continually deploy and integrate code
Reduced need for Pre-SIT
Increased code quality to SIT
Reduced SIT duration
Timeline
Drive testing & deployment efficiency
Increase testing and deployment automation
Introduce dedicated UAT testers
Reduce SIT and UAT durations
Clear testing backlog
Timeline
Cease merging sprints
Implement change management controls: Do not accept changes to requirements that would lead to merging sprints
Sprints no longer merged after sprints 26-27.
Sprint 28 the first single sprint release since Sprint 12.
Sep 2020
For 2 July
Mahesh, Subhash, team

## Slide 18: Program efficiency benchmark
    Benchmark based on what we have delivered for the money M1 spent (simple one slider as to what was the spent and what is delivered. Or for what we are delivering now, is M1 supposed to spend 100 but actually spending 80) – Very minimal 1 slider focusing on story point.
For 2 July
Ganesh

## Slide 19: Efficiency measurement and management using golden stories
Final story level story point estimates will be based on complexity, not effort.
Golden Stories used as comparison points to keep estimates comparable sprint over sprint.
Earlier T-shirt sizing and discovery & solutioning estimates based on person days as before.
Golden Stories serve as the benchmark for complexity-based estimation.
Every component technology has their own suite of mutually agreed golden stories.
Golden Stories from different component technologies aligned on size based on effort on the sprint N.
1
Digital Office quality audit as required to ensure story point values justified and no estimate inflation.
Efficiency increase visible when more story points = more complexity achieved per developer day.
Each component team’s use of time in a sprint (developer days) is measured as today.
Complexity based story points divided by used developer days gives an efficiency metric.
3
2
Define Golden Stories
Estimate complexity, not effort
Validate against use of time
For 2 July
Aaro
Mahesh, Ganesh,

## Slide 20
THANK YOU
COPYRIGHT 2020 M1 LIMITED. ALL RIGHTS RESERVED.